## Daily Report
FORMIS | [6 empty] | useformis.com
Construction Daily Report
Log the day's work, crew, equipment, and conditions. One report per day keeps the record straight.
How to use: fill in the shaded cells. Gray italic text shows examples of what to enter.
Project Information
Project |  |  |  | Project # |  | Report #
Date |  | Prepared by |  |  |  | Title
Weather | e.g. Clear, light wind |  | Temp (hi/lo) | 78 / 55 | Site conditions | e.g. Dry, accessible
Crew / Manpower on Site
Company / Trade | Workers | Hours | Work Area / Activity |  |  |  | Notes
e.g. True North Electric | 6 | 48 | Level 2 rough-in, east wing
Totals | 6 | 48
Equipment on Site
Equipment | Qty | Hours Used | Notes
Work Performed Today
Describe the day's work by trade and area...
Materials Delivered
Material | Qty | Supplier | Notes
Delays, Issues, or Conflicts
Note any delays, causes, and impacts...
Safety
Incidents? | Yes / No | Toolbox talk? | Yes / No | Details
Visitors / Inspections
e.g. City inspector, 10:30 AM, framing inspection passed
Sign-off
Prepared by |  |  |  | Signature |  |  | Date
Free template from Formis. This form also runs live in Formis with routing, approvals, and the project record. useformis.com/templates